## Sheet1
Suggestions for improvement | Status | Completed date | Signature
Replace water suction with a vacuum system (ALBANOVA) | completed | 2018-11-28 | KANJE
Replace water cooling with air cooling, eg reflux cooking (INFRA) | Ongoing (Tavast): Investigation (finished june 2019)
Switch to automatic water taps on lab (ALBANOVA) | Ongoing (Tavast): Investigation (finished june 2019)
Information on the school's intranet regarding the AV technology available in each meeting room. | completed | 2018-10-15 | GERLA
introduction of CBH nytt | completed | 2018-02-01 | FABRIZI
Revision of thr school's intranet | ONGOING |  | intranet Editors
Introduce more KLARA administrators at the school | completed | 2019-01-31 | TAVAST
Rutinerna för farligt avfall kompletteras med information om vem transportören kontaktar för att få transportdokumentet undertecknat. Infrastrukturansvarig gör en lista på kontaktuppgifter till personer som får uppdraget att signera transportdokumenten. | completed | 2018-06-18 | TAVAST
Head responsible KLARA should be able to see and edit in KLARA for the entire school | Compled - able to watch the whole school Ongoing- editing rights (finished June 2019 - TAVAST) | 2018-08-12 | TAVAST
Mercury thermometers in the lab | Ongoing (Everyone should be away from lab August 2019 - TAVAST responsible
Uppload Written Risk Assessments in KLARA | Miljö group can spread the info/Annie | 2019-01-01
Clean out old chemicals from course lab TR | Annie and Gustav for the course labs TR | 2019-09-01
Replace all old desicator pellets with new ones | Miljö group can spread the info/Annie | 2019-01-01